## RHW Action Plan
Goal: | Reduce the illness, disability and death caused by breast cancer in the Tri-County area.
Objectives: | 1. By 2019, reduce mortality rates by 3% as described in Healthy People 2020
Strategies | 1. Increase the rate of early stage breast cancer detection. (Community Guide)
2. Increase the proportion of newly diagnosed women who receive breast cancer treatment. (County Health Rankings)
Tasks | Strategy | TIMELINE | Responsible Leaders | Performance Indicators | Status as of xx/xx, 2018 |  |  | NOTES
[5 empty] | On Track | Some Activity | No Activity
our suggested 10 % improvement
1. Increase screening rates of mammograms for women | 1 | [6 empty] | (Community Guide)
1.a. Collect baseline data on number screening mammograms for women | 1 |  | hospitals | targeting women age 40-64; also get baseline mortality rate for our specified age group |  |  |  | target from 73.7% to 81.1 or 10% improvement (National health Interview Survey)
1.b. Choose a common set of community screening age guidelines | [7 empty] | we discussed baseline at age 40 and yearly
1.c. Educate providers on common set of community guidelines | 1
1.d. Promote patient reminder recall systems at providers | [7 empty] | (Community Guide)
1.e. Provide outreach to women | 1 | [6 empty] | group education, 1 on 1 - Comm Guide
1.e. Provide culturally adapted outreach education to disparate populations | 1 | [6 empty] | disparity - lack of healthcare coverage, low SES, race, rural have lower screening rates; adapted care improves health outcomes and decreases disparities (Co Hlth Rankings)
1.f. Prmote access to funding/IBCCP/ACA | 1
1.g. promote a medical home for women | 1 | [6 empty] | increase access, continuity, quality care (CO Hlth Rankings)
2. Increase baseline (1st time) screening rates of mammograms for women | 1
2.a. Collect data on number of baseline (1st time) mammograms for women |  |  | hospitals
2.b. Provide access to genetic counseling for at risk women | ? |  | Il Cancer Care |  |  |  |  | (Good to have but does this increase screeenig rates??)
2.c. Provide at-risk assessments to women | ? |  | OSF |  |  |  |  | (Good to have but does this increase screeenig rates??) OSF provides this - when? At outreach? When getting mamm?, do other hospitals need to do this?
3. Increase proportion of newly diagnosed women with early stage breast cancer who receive timely breast cancer followup treatment | 2 | [6 empty] | (Co Hlth Rankings - adherence to treatment)
3.a. Collect data on number of early stage receiving followup treatment | 2 |  | hospitals
3. b. Establish patient navigator programs for breast cancer patients in all hospitals | 2 | [6 empty] | improve adherence to treatment receipt, decrease disparities, eliminates barriers (Co Hlth Rankings)
3.c. Patient navigators provide adapted counseling/assistance to newly diagnosed breast cancer cases | 2 | [6 empty] | to increase receipt of followup treatment Co Hlth Rankings)

## Workgroups
WORKGROUP | INTERVENTION FOCUS | DESCRIPTION | STRATEGIES
1 | Behavioral & Biomedical | Behavioral Interventions: Behavioral risk-reduction interventions aim to reduce risk behavior of persons with STIs/HIV and/or persons who are at high-risk for contracting an STI/HIV by promoting behaviors such as using condoms, avoiding sexual practices that are most likely to result in transmission to others, and not sharing drug-injection equipment. Bio-behavioral Intervention: An intervention grounded in a conceptual model that includes psychological, behavioral, and biological components (e.g., medication adherence, pre-exposure prophylaxis). Biomedical Intervention: The use of medical, clinical, and public health approaches designed to moderate biological and physiological factors to prevent infection, reduce susceptibility to infection, and/or decrease infectiousness. Biomedical risk-reduction interventions include antiretroviral medications that persons with HIV can take to prevent transmitting HIV as well as antiretroviral medications that their uninfected partners can take to prevent acquiring HIV.
2 | Public Health | Time-tested protocols used by public health practitioners in the prevention, screening, diagnostic, or treatment processes. Based on concepts of primary, secondary, and tertiary prevention and may include individual risk counseling, diagnostic testing, and partner services.
3 | Social Marketing | The use of marketing theory, skills, and practice to achieve social change, promote general health and raise awareness. Social marketing uses tools and techniques such as focus groups and surveys to discover barriers, social norms, and incentives to change behavior. For example, social network programs can use social marketing techniques to test social marketing strategies to reach persons with undiagnosed STIs/HIV infection.
4 | Structural | Interventions designed to implement or change laws, policies, physical, social or organizational structures, or standard operating procedures to effect environmental or societal change.
S

## Tracking Log
ITEM/ISSUE | SUGGESTED BY/ RESPONSIBLE PARTY | DATE INITIALLY DISCUSSED | DATE OF MOST RECENT DISCUSSION | REVISIT DATE | STATUS
CenteringPregnancy MOU | M. Adamson | 2017-11-01 |  |  | Discussed with Administrator
Social media: YouTube Videos |  | 2017-11-29
Hosting panel event