## Cancer Lung Radon
Goal: | Reduce the illness, disability and death caused by lung cancer in the Tri-County area.
Objectives:
1. By 2019, reduce mortality rates by 3% as described in Healthy People 2020.
Strategies
1. Increase the proportion of homes with an operating radon mitigation system for persons living in homes at risk for radon exposure.
| Strategy | TIMELINE | Responsible Leaders | Performance Indicators | Status as of xx/xx, 2018 |  |  | NOTES
[5 empty] | On Track | Some Activity | No Activity
Interventions/Tasks
1. Inform the public of radon in the Tri-county area. | 1
1.1 Create a Radon Resource Guide for Tri-county region. | 1 |  |  | Guide created |  |  |  | Radon mitigation system installation companies and distributors of radon test kits; https://www.illinois.gov/iema/NRS/Radon/Pages/RadonIllinois_nonFlash.aspx
1.1.a Distribute the Guide to the public | 1 |  |  | # Guides distributed
1.2 Attend outreach activities in the community | 1 |  |  | # outreach activities; # population reached
1.3 Conduct a social media campaign | 1 |  |  | # messages posted; # population reached; # engaed through comments/likes/shares
2. Increase the proportion of homes that conduct radon tesing. | 1
2.2 Provide screening test kits. | 1 |  |  | # kits provided
2.2a Secure funding as needed for kits. | 1 |  |  | # kits available |  |  |  | write grant to purchase kits; sell kits
2.3 Partner with tobacco programs and Healthy Homes programs to promote screening. | 1 |  |  | # partners |  |  |  | Higher risk for smokers and radon (85% of radon lung cancer are smokers)
2.4 Track the data. | 1 |  |  | # tests conducted per county (IEMA, Health Dept Air Check) |  |  |  | screening or contractor?
3. Increase the installation of radon mitigation systems in high-risk homes. | 1 | [6 empty] | some evidence County Health Rankings (reduced exposure, improved health outcomes)
3.1 Review the policies on mitigation of homes. | 1 |  |  | policy reviewed
3.2 Partner with key stakeholders on mitigation promotion of policy and assurance. | 1 |  |  | # partners
3.3 Provide outreach to inform the public of mitigation professionals. | 1 |  |  | # of campaigns/interventions; # people reached |  |  |  | health fairs, social media campaign, mailings, posters
3.3a Assess and assure workforce capacity. | 1 |  |  | capacity to install
3.4 Collect data on number of mitigation systems installed. | 1 |  |  | Target is 30% HP2020 |  |  |  | IEMA and local mitigation installers (IEMA site); Baseline: 10.2% of homes with radon levels of 4 pCi/L or more prior to mitigation installed a mitigation system in 2007. (HP2020)